## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-11 | Setup of project (JDK,Spring boot) | MUST HAVE |  | Santhosh Kumar S | 3- Completed
S1 | S1 | US-12 | Implement Task CRUD using themeleaf UI | MUST HAVE | US-11 | Santhosh Kumar S | 3- Completed
S1 | S1 | US-13 | Add filter,sorting and pagination in UI | MUST HAVE | US-12 | Santhosh Kumar S | 3- Completed
S2 | S2 | US-21 | Add enums(Status,priority)+UI improvements | MUST HAVE | US-12 | Santhosh Kumar S | 3- Completed
S2 | S2 | US-22 | Implement REST APIs for Task CRUD | COULD HAVE | US-11 | Santhosh Kumar S | 3- Completed
S2 | S2 | US-23 | Add REST filtering,sorting and pagination | COULD HAVE | US-21 | Santhosh Kumar S | 3- Completed
S2 | S2 | US-24 | API testing via Postman+final cleanup | MUST HAVE | US-22 | Santhosh Kumar S | 3- Completed
S3 | S3 | US-31 | Authentication and authorisation | MUST HAVE | US-11 | Santhosh Kumar S | 3- Completed
S3 | S3 | US-32 | Integration of Email Api | MUST HAVE | US-31 | Santhosh Kumar S | 3- Completed
S3 | S3 | US-33 | Implementing Session and Jason web token | MUST HAVE | US-32 | Santhosh Kumar S | 3- Completed
S4 | S4 | US-41 | Implementation of task tracking | MUST HAVE | US-12 | Santhosh Kumar S | 3- Completed
S4 | S4 | US-42 | Build dashboard with visuals analytics | MUST HAVE | US-41 | Santhosh Kumar S | 3- Completed
S4 | S4 | US-43 | Adding user profile and password management | MUST HAVE | US-41 | Santhosh Kumar S | 3- Completed
S4 | S4 | US-44 | Adding reminder settings export data | MUST HAVE | US-32 | Santhosh Kumar S | 3- Completed
3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 63 | 5 | 5 | 5 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 4
SPRINT 1 BACKLOG
US-11 | T-1 | Dowloading and installing JDK 17 ,Spring Boot Setup | 2025-11-27 | 2025-11-28 | Santhosh | Setting up | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-2 | Installing and setting up Intellij and setting up project environment with spring boot | 2025-11-28 | 2025-11-28 | Santhosh | Setting up | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-3 | Making TaskController and appling CRUD operation | 2025-12-01 | 2025-12-09 | Santhosh | coding | Completed | 5 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-4 | Adding APIs pages for add,view,edit, delete and posting to github | 2025-12-02 | 2025-12-09 | Santhosh | coding | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0
US-12 | T-5 | Setting up Sql and connecting to spring boot | 2025-11-05 | 2025-11-06 | Santhosh | coding | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
US-13 | T-6 | Appling Pagination ,filters and sorting | 2025-12-09 | 2025-12-10 | Santhosh | coding | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
US-21 | T-7 | Adding enum's and working on css ,html | 2025-12-11 | 2025-12-12 | Santhosh | coding | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-8 | Adding RestCntroller and Applying CRUD operation | 2025-12-12 | 2025-12-15 | Santhosh | coding | Completed | 5 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T-9 | Adding Rest APIs pages for add,view,edit, delete | 2025-12-16 | 2025-12-18 | Santhosh | coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-23 | T-10 | Adding filter and sorting for Rest APIs | 2025-12-19 | 2025-12-23 | Santhosh | coding | Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0
US-24 | T-11 | Api testing via postman | 2025-12-23 | 2025-12-24 | Santhosh | testing | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
US-24 | T-12 | Few api addition and Ui improvement | 2025-12-24 | 2025-12-25 | Santhosh | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
US-31 | T-13 | Adding authcontroller | 2025-12-26 | 2025-12-27 | Santhosh | coding | Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-14 | Adding email service | 2025-12-28 | 2026-12-28 | Santhosh | coding | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-15 | Implementing sending and verifying otp | 2025-12-29 | 2025-12-30 | Santhosh | coding | Completed | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-16 | Working on Frontend of Authenticating | 2025-12-31 | 2026-01-03 | Santhosh | coding | Completed | 4 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-33 | T-17 | Implementing Sessions for task viewing of respective accounts | 2026-01-06 | 2026-01-09 | Santhosh | coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US-41 | T-18 | Implementing tracking systems based on status ,priority and duedates | 2026-01-12 | 2026-01-13 | Santhosh | coding | Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-42 | T-19 | Adding a dashboard overview for trackings | 2026-01-13 | 2026-01-15 | Santhosh | coding | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-42 | T-20 | Working on frontend for task overview and recent tasks | 2026-01-15 | 2026-01-17 | Santhosh | coding | Completed | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T-21 | Securing otp and password with bcrypt and adding security config | 2026-01-19 | 2026-01-20 | Santhosh | coding | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-43 | T-22 | adding profile and editing profile details | 2026-01-21 | 2026-01-21 | Santhosh | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-44 | T-23 | Adding reminder setting | 2026-01-22 | 2026-01-23 | Santhosh | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
US-44 | T-24 | Adding calender view and improving visuals with list view and card view | 2026-01-24 | 2026-01-25 | Santhosh | coding | Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
US-44 | T-25 | Implementing export option through email and dowload options | 2026-01-25 | 2026-01-26 | Santhosh | coding | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-10-27 | 2025-12-10 | Santhosh Kumar S | improving the task management System |  | UI Improvements | worked on add,edit,delete and filters and sorting
2 | Sprint 2 | 2025-12-11 | 2025-12-24 | Santhosh Kumar S | implementation of Rest api |  | Testing | implemented RestController and starting testing
3 | Sprint 3 | 2025-12-26 | 2025-01-09 | Santhosh Kumar S | implementation of authentication and authorisation |  | Testing and verifying | Providing user login,sign up options and making sure they work properly
4 | Sprint 4 | 2025-01-12 | 2025-01-23 | Santhosh Kumar S | improvement of UI and dashboard implementation |  | UI Improvements | improving the UI and adding dashboard and reminder options
5
6
7